## 10-17
City Glass Company |  |  |  | MB7 | MB7 | CTD/Budget | MB7 | Cont/Budget |  |  |  | Prof/Cont | MB7 | Earned-Billed | PGP x % Comp |  |  |  | Earned GP - Previous Earned GP |  | CTD - Previous Month |  |  |  | Cont - Billed |  | Budg - CTD |  | CTC - BOH
2017-10-31 | [8 empty] | HIDE | [5 empty] | Gross Profit |  |  |  |  | CHANGE FROM LAST MONTH |  | BASELINE
|  |  |  | Costs To | Current | % | Adj | Current | Orig | Orig | Bid | Current |  | (Over)/Under |  |  |  | Complete |  |  |  | 1.25 | Min Mark Up |  | Remaining |  | Costs to | Remaining | Job
Job | ST | PM | LM | Date | Budget | Comp | Contract | MU | Budg | Cont | MU | Margin | Billed | Billing | Earned | Projected | Bid | Delta | GP | Margin | CTD | Costs | GP | Delta | Revenue | BOH | Complete | GP | Borrow | Job# | Costs | / | Budget | = % | X | Contract | = | Earned | - | Billed | = | Over/Under
Project A | NE | JD |  | 335001.67 | 447338.21 | 74.89% | 563920 | 1.2606 | 428081 | 495000 | 1.1563 | 20.67% | 385848.15 | 36471.54 | 87305.5184 | 116581.79 | 66919 |  | 2482.5943 | 0% | 9526.01 | 451136 | 112784 | 3797.79 | 141612.8116 | 178071.85 | 112336.54 | 65735.31 | 0 | Project A | 335001.67 |  | 447338.21 | 74.89 |  | 563920 |  | 422319.69 |  | 385848.15 |  | 36471.54
Project B | NE | JD |  | 1023710.92 | 1023710.92 | 100% | 1307147.83 | 1.2769 | 985000 | 1191800 | 1.2099 | 21.68% | 1235310.83 | 19289.66 | 283436.91 | 283436.91 | 206800 | 76636.91 | 31695.7199 | 0.4269% | 91160.57 | 1045718.264 | 261429.566 | 22007.344 | 0 | 71837 | 0 | 71837 | 0 | Project B | 1023710.92 |  | 1023710.92 | 100 |  | 1307147.83 |  | 1254600.49 |  | 1235310.83 |  | 19289.66
Project C | NE | JC |  | 81513.06 | 90851.84 | 89.72% | 230054 | 2.5322 | 47974 | 60760 | 1.2665 | 60.51% | 227084 | -20679.55 | 124893.3871 | 139202.16 | 12786 |  | -491383.6429 | 42.7% | -2762576.91 | 184043.2 | 46010.8 | 93191.36 | 23647.5529 | 2970 | 9338.78 | -6368.78 | 6368.78 | Project C | 81513.06 |  | 90851.84 | 89.72 |  | 230054 |  | 206404.45 |  | 227084 |  | -20679.55
[5 empty] | 1561900.97 |  | 2101121.83 | 1.3452 |  |  |  | 25.66% |  | 35081.65 | 495635.8155 |  |  | 76636.91 | -457205.3287 | [5 empty] | 165260.3645 | 252878.85 | 121675.32 | 131203.53 | 6368.78
Note on T2: Change Formula to look at previous month
Note on O3: Earned - Billed
Note on P4: Projected GP x % Comp
Note on Z4: Adj. Cont - CTD - Earned GP
Note on AB4: Current Budget - CTD
Note on AD4: Cost to Complete - B.O.H.

## 9-17
City Glass Company |  |  |  | MB7 | MB7 | CTD/Budget | MB7 | Cont/Budget |  |  |  | Prof/Cont | MB7 | Earned-Billed | PGP x % Comp |  |  |  | Earned GP - Previous Earned GP |  | CTD - Previous Month |  |  |  |  | Cont - Billed |  | Budg - CTD |  | CTC - BOH
2017-09-30 | [9 empty] | HIDE |  |  |  |  | Gross Profit |  |  |  |  | CHANGE FROM LAST MONTH |  | BASELINE
|  |  |  | Costs To | Current | % | Adj | Current | Orig | Orig | Bid | Current |  | (Over)/Under |  |  |  | Complete |  |  |  | 1.23 | Min Mark Up | Incentive |  | Remaining |  | Costs to | Remaining | Job
Job | ST | PM | LM | Date | Budget | Comp | Contract | MU | Budg | Cont | MU | Margin | Billed | Billing | Earned | Projected | Bid | Delta | GP | Margin | CTD | Costs | GP | 5% | Delta | Revenue | BOH | Complete | GP | Borrow
Project A | NE | JD |  | 325475.66 | 447338.21 | 72.76% | 563920 | 1.2606 | 428081 | 495000 | 1.1563 | 20.67% | 355148.15 | 55160.04 | 84822.9241 | 116581.79 | 66919 |  | 2902.0314 | 0% | 11135.44 | 458471.5447 | 105448.4553 |  | 11133.3347 | 153621.4159 | 208771.85 | 121862.55 | 86909.3 | 0
Project B | NE | JD |  | 932550.35 | 1023710.92 | 91.1% | 1300060.83 | 1.2699 | 985000 | 1191800 | 1.2099 | 21.26% | 1187647.83 | -3292.41 | 251741.1901 | 276349.91 | 206800 |  | 2684.4555 | 0% | 9944.3 | 1056960.0244 | 243100.8056 |  | 33249.1044 | 115769.2899 | 112413 | 91160.57 | 21252.43 | 0
Project C | NE | JD |  | 2844089.97 | 2844089.97 | 100% | 3460367 | 1.2167 | 2748591 | 3469170 | 1.2622 | 17.81% | 3460367 | 0 | 616277.03 | 616277.03 | 720579 | -104301.97 | -19405.3014 | -0.5466% | 16737.15 | 2813306.5041 | 647060.4959 |  | -30783.4659 | 0 | 0 | 0 | 0 | 0
0
[5 empty] | 4315139.1 |  | 5324347.83 | 1.2339 |  |  |  | 18.95% |  | 51867.63 | 952841.1442 |  |  | -104301.97 | -13818.8145 | [5 empty] | 13598.9732 | 269390.7058 | 321184.85 | 213023.12 | 108161.73
[26 empty] | GP on BL | 6940899.2499 | 30.56%
Note on T2: Change Formula for last month
Note on O3: Earned - Billed
Note on P4: Projected GP x % Comp
Note on AA4: Adj. Cont - CTD - Earned GP
Note on AC4: Current Budget - CTD
Note on AE4: Cost to Complete - B.O.H.